Team Euclid Project Plan
# Version History
Version	Author(s)	Description	Version Date
Version 1	Jess VanDerwalker, / Ben Carr, / Benjamin Huddle, Aaron Skomra, / David Snyder, / Braden Wooley	Initial version	2011-11-26

# Review History

Reviewer(s)	Version	Comments	Date

# Approvals

Approved By	Version	Signature Date

1. Project Description
Our main goal is to create a rootless compositing window manager on OS X utilizing XCB. This includes basic window manager functionality such as movement, minimizing, maximizing, and closing. Additionally, processing of native input such as mouse and keyboard events is required. X11 windows should model and be drawn as native platform windows. A very important component of the project is to “library-ify” as much of the code as possible so that it can be system independent.

A discussion of jargon pertinent to the project follows:
Rootless - To produce a rootless window, no existing root window will be rendered. However, children of the root window will be present. As we communicate with the X server, a root window will be active in memory but will not be rendered.

Compositing & Damage - Our project will make use of the Comoposite and Damage X protocol extensions. The Composite extension will set up root window position relative to other windows. The Damage extension deals with changes in the atmosphere, mainly dealing with regard to window coordinates. We will be doing manual compositing which renders children of root window but not the root itself.

Window Manager - Our project will emulate basic window manager functionality. This includes minimizing, maximizing, resizing, and closing a window. This will be done with mouse events and input from the keyboard.
# 2. Deliverables
The deliverables for this project include the five milestones numbered 0-4. The final deliverable is a git repository containing a rootless, composting window manager which takes input. This software will utilize XCB and run on OS X.
# 3. Key Assumptions and Constraints, References
Assumptions
The Project Plan is a living document, subject to editing in response to changes in requirements, to events described in the Risk Mitigation section of this document, or other unforeseen events.
Apple hardware with OS X installed will be made available to the team for the development and testing of the deliverables
Constraints
- The deliverables must be able to compile and run on OS X
- The “library” functionality will be, as much as possible, general and platform independent
- The “library” code will be written in C interfacing with XCB. The interface that this “library” provides will be demonstrated in an application written in Objective-C
- An Open Source license will be used
# 4. Work Breakdown Structure
Please see Appendix A for the current Work Breakdown Structure for the project. A version can also be found at http://web.cecs.pdx.edu/~jvanderw.
# 5. Milestones
There are currently six milestones for the project.

Milestone	Scheduled Completion Date

Initial version of Project Plan..............................................................................November 28, 2011
At this milestone, the initial version of the Project Plan (this document) and its attendant material will be completed. It is understood that the Project Plan is a living document and that the submitted content may change as the project progresses.

Milestone 0 - Learn XCB and API for OS X …....................................................December 2, 2011
At this milestone, the team shall show the ability to work with XCB and the OS X development environment by being able to create a simple (i.e. without input) X window on OS X. This milestone also includes being able to compile the X Server from current X.org code and verify that it is working on the development machines. A component of this milestone is configuring xorg.conf for use with the dummy driver.

Milestone 1 - Rooted window with Damage …......................................................January 31, 2012
This milestone involves retrieving the contents of the OS X root window and displaying said contents. This will be done via a “GetImage” request. Though it does include the use of Damage, this milestone does not require the use of Composite or XTest.

Milestone 2 - Rooted window with input …..........................................................February 24, 2012
Milestone 3 is not dependent on milestone 2 and the two tasks could be done in parallel, if scheduling permits. This milestone delivers an application that accepts input from the OS X event handler and then passes that input to the X server (via libxcbtest). The X server will subsequently pass the input to the correct application.

Milestone 3 - Rootless window without input	…..................................................February 28, 2012
This milestone delivers rootless windows and is essential to the expected performance and feel of the desktop. At this point, much of our understanding of rootless windows comes through examples of the behavior of rootless windows. Rootless windows demonstrate the ability to be interleaved with native windows. Also, elements of rootless windows, such as drop down menus, can also react to native events in other windows (eg. retracting drop down menu when losing focus).

Milestone 4 - Rootless window with input …............................................................March 15, 2012
This milestone synthesizes milestones 2 and 3. In this final required milestone, our project will arrange the coordination of the previous two milestones. This coordination includes presenting the correct coordinates to the X server as well as presenting a coherent stream of information to the X server.
# 6. Calendar / Gantt Chart
Please see Appendix B for a Gantt chart of the project tasks. Note that a version is also available online at http://web.cecs.pdx.edu/~jvanderw.
# 7. Meetings and communication
Our weekly meetings take place on Monday evenings at 6:30pm. These meeting are frequently attended by one or more of our sponsors and has been one of the ways we have stayed in contact with them. In addition to the weekly meetings that we have, we are able to stay in contact with our sponsors through email. We have a group email list that every team member and sponsor is subscribed to: euclid@cecs.pdx.edu. As a team we primarily communicate through the group email list, but we also send individual emails to one another as the need arises. #euclid, a channel on the school irc server, has also been created as another way for us to communicate with each other. For task management we use Redmine’s issue tracker to communicate what needs to be done, when it should be done, and who is in charge of doing it.
# 8. Resource Identification
Please see Appendix C.1 through C.6 for detailed resource identification and usage.
# 9. Configuration Management - asset tracking
For this project there are three main electronic artifacts we need to keep track of:
Code
- We are using a Redmine account (Euclid) acquired from the PSU Computer Action Team (CAT). All of the code written for this project will be hosted at the CAT’s project hosting server (projects.cecs.pdx.edu) using a git repository which has been configured to work with Redmine.
- The Redmine issue/ticket system will be integrated with the repository such that branches will be created based on specific issues (i.e. bug fixes, implementation of new features/functions). By utilizing the correspondence feature of the ticket system, issues can be handled on branches independent from the master branch until they are completed. The repository moderator will be responsible for merging final versions of branches to the master branch. This process will include checking the ticket system to see the discussion about what the issue was, and also confirming that all merge conflicts are resolved properly. A detailed description for this process will be located in the Redmine Wiki for all team members to view.
- A Github account (TeamEuclid) has also been created to store the repository. Using a post-receive git hook, any pushes to the repository stored at projects.cecs.pdx.edu will immediately get pushed to the Github account. This process has two main purposes:
  - Keep a working backup of the code/repo somewhere outside of PSU if a catastrophe occurs at projects.cecs.pdx.edu
  - Make this code publicly available/viewable since this will ultimately be an open source product.
Daily (at 1am) a script will run on a secure PSU server which executes a pull for the repository and creates a tarball of the entire repository. This tarball will be stored in a backup directory on the server. Weekly (on Sundays) the lead System Administrator will create a backup CD of the current weeks tarballs. The CD will be delivered to another team member (at our Monday meeting) who will be responsible for storing the disks in a safe place outside of PSU. The CD will also contain the Mailman archives (see Mailing list section below). The lead Systems Administrator will be responsible for ensuring that the data can be retrieved from the disk before delivering to the other team member.

Mailing List
- Our mailing list is configured such that a daily archive is created (accessible by all mailing list subscribers). Weekly (On Sundays), the lead Systems Administrator will download these archives and create a tarball and store it in at a secure server at PSU. At this time the lead will also create a backup CD which will be delivered to another team member (at our Monday meeting) who will be responsible for storing the disks in a safe place outside of PSU. The lead Systems Administrator will be responsible for ensuring that the data can be retrieved from the disk before delivering to the other team member.
- If for some reason the archives are not being created properly (by Mailman), the lead Systems Administrator will be responsible for first fixing the problem and secondly manually creating an archive from the emails that were sent to the mailing list (which are stored in all members email boxes).

Documentation
While documentation is being prepared, it will be stored in Google Docs that all team members have access to. As revisions are created, the Documentation Lead will be responsible for moving files from Google Docs to the team repository at projects.cecs.pdx.edu.
# 10. Roles and Responsibilities
Jess VanDerwalker: Team Lead, Implementation
As team lead, Jess is responsible for managing the project and the team. This includes overseeing the scheduling of tasks, reporting of project status, and evaluation of team member performance. Jess is also responsible for insuring team members have the resources and tools necessary for them to complete their assigned tasks. In addition, Jess must work closely with the project sponsors, the Capstone lead, and the team to set milestones and deliverables. An integral part of this role is generating and maintaining the calendar, schedule, and significant parts of the Work Breakdown Schedule.
As an implementer, Jess will be responsible for segments of the code for which he has been made responsible as detailed by the work breakdown schedule.

﻿Benjamin Huddle: Verification and Validation
The verification and validation is the testing of the software to verify that the product meets the specifications and goals of our sponsors. Ben will validate that our product fulfills its intended purpose. This is usually accomplished by a series of tests which pertain directly to the specifications of the project proposal. Ben will also compare our product against our initial documents and requirements to see if it meets the criteria of the proposal.
As an implementer, Ben will be responsible for software implementation as detailed in the work breakdown structure.

David Snyder: Software Architect
The software architect decomposes the requirements of the software system into its high-level components. David will be responsible for the aspects of software decomposition that include system context, module decomposition and logical view, as well as dynamic process view and code architecture and execution. David will describe the client in terms of the interface that it presents to application software, as well as its interaction with the X Server, and reliance on libraries such as XCB and Xlib. David is also responsible for module decomposition and logical view which involves decomposing the software into smaller substructures, and describing the relationships between each module. The software architect will also produce the Architecture Decisions Document as well as the physical organization of the software components.
In addition to the role as software architect, David will bear equal responsibility with the other team members in implementing the project.

Ben Carr: Systems Administration
Ben will manage and administer the Redmine account, and the Github account which will be synced with Redmine repo. Ben will also administer Mailman and the on campus computers we utilize (e.g. OS, software install, etc) as well as the computers we may receive from our sponsor (e.g. OS, software install, etc). Ben will also be in charge of making sure that our documentation, code and mailing list are backed up. These items will be backed up daily onto a machine, or in to the cloud as necessary. Ben will verify these backups to make sure that they are working. The weekly verification will also include copying weekly backups onto physical media (compact disc, external hard drive) which Ben will keep off campus.
As an implementer, Ben will be responsible for software implementation as detailed in the work breakdown structure.

Braden Wooley: Design Role & Implementation
As designer, Braden will work with the architect to create a more detailed, fine-grained design. From the architects module decomposition and logical view Braden will take this higher level, module design and determine how the modules will work. At a lower level, Braden will be responsible for selecting the algorithms and data structures that we will use along with any classes or modules. Braden will help in the creation of a data flow analysis along with the creation of other design documents.
As an implementer, Braden will be responsible for software implementation as detailed in the work breakdown structure.

Aaron Skomra: Documentation, implementation
As documentation lead, Aaron will be responsible for coordinating and assigning documentation tasks. Aaron will also verify the integrity of the documentation by ensuring that the information is organized within an individual document as well as that the documentation as a whole is organized into a meaningful structure. Aaron will also ensure that the code is internally documented. Aaron will edit the documentation for content, and to a reasonable degree, edit the documentation for grammar, style, and consistency. Part of the documentation effort will produce, in conjunction with the team, this project plan.
As an implementer, Aaron will be responsible for software implementation as detailed in the work breakdown structure.

# 11. Risk Management
# Personnel
Risk:
Team Member leaves the Capstone program
Mitigation:
Losing a team member in the middle of the project will require an adjustment to the schedule and a reassessment of milestone deliverable and dates. This will necessitate conversations with the sponsors to reduce the scope of the work or change the definition of the deliverable. Depending on when the individual leaves the program, this may not require many changes in the overall project since some slack time has been allotted in the schedule.

Risk:
Team Member is unavailable for two weeks of the project
Mitigation:
As the schedule currently stands, the team is set to deliver its final milestone a week before the end of the project. In addition, the schedule assumes 12.5 hour work weeks while the required amount of work expected from team members is 15 hours per week. This slack time should allow the team to absorb the loss of an individual for a period of two or less weeks. If the time is longer than that, then the result would be closer to loosing the team member completely, and the mitigation would then be the same as a team member leaving the Capstone program.

There are two special cases that warrant consideration: the loss of the Project Lead and the loss of the System Administrator. In the first situation, one of the team members will need to temporally step into the lead role. Assuming the Project Plan and Work Breakdown Schedule have been maintained, the temporary lead will have the tools necessary to keep the project on track. Who takes this role will need to be discussed with the Capstone Lead, and ultimately require their approval.

In the case of the loss of the System Administrator, responsibility for maintaining the repository and generating backups will need to be quickly assigned to another team member. Again, the slack time in the schedule should allow this - the important consideration here is to make sure backups continue.
# Sponsor
Risk:
Sponsors abandon the project.
Mitigation:
The team is fortunate in that we are being sponsored by a group of individuals working within the open source community. It is very unlikely that all three sponsors would abandon the project. Even if that was the case, we are again fortunate that the Capstone Lead, Bart Massey, is familiar with many aspects of the code we will be working in. So, it is possible that, with some guidance from Bart Massey, that the team could continue with the project. Since the project itself is open source, the loss of one of the sponsors may, to a degree, be alleviated by the eventual release of the code to the X.org community.
# System Administration
[Ben - This one occurred to me]
- One of the Apples we get breaks
# Architecture and Design
Risk:
A milestone is missed
Mitigation:
One purpose of regular milestones is to mitigate other risks associated with architecture and design: describing a module with incorrect behavior, and deviating from the schedule. By breaking the project into multiple 2-week milestones, we can, with feedback from the sponsors a) verify that each newly introduced component or functionality contributes to the final deliverable and b) be held to a series of short-term milestones to aid in the successful and timely completion of the project.

In the event that a milestone slips, several mitigation strategies can be assessed. First, there already is some slack-time incorporated into the schedule, and with careful planning of subsequent milestones, the missed deadline may be absorbed into the schedule while still achieving the desired deliverable. Second, although each milestone is currently allocated the same 2-week time frame to complete, it is likely that some milestones may take more or less time to complete. In the event of an overdue milestone, it will be necessary to determine if the functionality for any of the subsequent milestones is light enough so that the present milestone may be allowed to slip somewhat, while the scheduled time for a subsequent milestone, reduced. Lastly, if no other options are available, the deliverable will need to be reassessed, and at least some functionality of the future milestones reduced

# 12. Quality Assurance and Testing
We will be verifying that all our milestones meet the specifications posted in section 5 of this document and also in the User Requirements document. There will be a set procedure of tests to validate that our software meets the sponsor’s specifications. We will individually verify components of our software. At the end of each two week period we will validate that the milestone meets the sponsor’s specifications.
# 13. Deployment
Everything we create will be placed into an open source, Github repository which is available to all. The repository will contain our “library-ified” code as well as the Mac OS X rootless application. The repository will contain a description of what the project does. The repository will contain all the necessary files and documents that are required to install and run the software that we develop including, but not necessarily limited to, a README.